## Checklist
QA Checklist
Project Name / URL |  | https://demoblaze.com/index.html
Tester Name |  | Basel Abdullah
Software Version |  | V 1.0
Date |  | 2026-02-12
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Expected Result | Actual Result | Status | Priority
TC_001 | Signup | Verify signup with empty credentials | User is on signup page | 1- Keep username and password fields empty. 2- Click on "Signup" button. | Error message asking to fill the username and password | Error message appeared saying "Please fill out Username and Password." | Pass
TC_002 | Signup | Verify signup with already registered user | User is on signup page | 1- Fill credentials of an already registered user. 2- Click on "Signup" button. | Error message saying that the user is already registered | Error message appeared saying "This user already exist." | Pass
TC_003 | Signup | Verify signup with a very short username | User is on signup page | 1- Fill the username field with a short name (2 or 3 characters). 2- Click on "Signup" button. | Error message saying that the username is too short and should contain a minimum number of characters | User signed up successfully | Fail | Medium
TC_004 | Signup | Verify signup with username containing only numbers | User is on signup page | 1- Fill the username field with only numbers. 2- Click on "Signup" button. | Error message saying that the name must contain letters | User signed up successfully | Fail | Medium
TC_005 | Signup | Verify signup with valid credentials | User is on signup page | 1- Fill the username and password fields with valid credentials. 2- Click on "Signup" button. | Signup completes successfully | User signed up successfully | Pass
TC_006 | Login | Verify login with empty credentials | User is on login page | 1- Keep username and password empty. 2- Click on "Login" button. | Error message asking to fill the username and password | Error message appeared saying "Please fill out Username and Password." | Pass
TC_007 | Login | Verify login with invalid credentials | User is on login page | 1- Fill the username and password fields with credentials of an unregistered user. 2- Click on "Login" button. | Error message saying that there is no user with these credentials | Error message appeared saying "User does not exist." | Pass
TC_008 | Login | Verify login with valid credentials | User is on login page | 1- Fill the username and password fields with valid credentials of a registered user. 2- Click on "Login" button. | Loggin user in successfully | User logged in successfully | Pass
TC_009 | UI | Verify text color when hovering over nav bar elements | User is on home page | 1- Move the mouse near a nav bar element. 2- Hover the mouse over the element. | Text color should change to a color that is consistent and different from the background color | Text color changed to a very close color to the background | Fail | Low
TC_010 | Home | Verify separation of products categories | User is on home page | 1- Choose a product category. 2- Navigate to the end of products. 3- Click "Next" or "Previous" button. | Only products of the selected category should appear | Products from other categories appears | Fail | High
TC_011 | UI | Verify responsivity for mobile phones | User is on mobile phone | 1- Open the website on the mobile phone. | Website's UI should appear correctly on mobile screen | There is text-overflow in the nav bar elements on a mobile screen | Fail | Low
TC_012 | Home | Check product details loading speed | User is on home page | 1- Click on a product. | Loading should take a reasonable time | Loading takes a long time | Fail | High
TC_013 | Product Details | Order a product without logging in | 1- User is on home page 2- User is not logged in | 1- Click on a product. 2- Click on "Add to cart". | Error message saying that the user should be logged in to be able to order a product | Product added to cart | Fail | High
TC_014 | Cart | Check place order when cart is empty | 1- User is on cart page 2- Cart is empty | 1- Click "Place Order" button. | Error message saying that the cart is empty and ask the user to add at least one product | A form for placing an order appears | Fail | Medium
TC_015 | Cart | Check place order form fields | 1- User is on cart page 2- Cart has at least one product | 1- Click "Place Order" button. | A form containing only order related fields appears | A form containing unnecessary fields like "Month" and "Year" appears | Fail | Low
TC_016 | Cart | Check order confirmation pop-up | 1- User is on cart page 2- Cart has at least one product | 1- Click "Place Order" button. 2- Fill the form with valid data. 3- Click on "Purchase". | A pop-up with valid information about the order appears | A pop-up appears with an incorrect order date | Fail | Medium

## Status (hidden)
PASS
FAIL
N/A
N/E